# K12Technology Roadmap

## K12 Modernization

IT Stakeholder Presentation
October 2025

- College Foundation, Inc.

- North Carolina SEAA Programs

- Timeline: October 15, 2025 - May 1, 2026

## Agenda

- Executive Summary – Project overview and timeline

  - Modernizaton Scope

  - Core Capabilities

  - Platform Overview – Complete system scope

  - Tools

  - Infrastructure

  - Cross-Cutting Concerns

  - 3rd-Party Integrations

  - Data Migrations

- Complete Feature Inventory – All core capabilities

- Risk Assessment – Critical areas and mitigation

- Success Criteria – Delivery milestones and quality metrics

- Next Steps – Execution and monitoring

## Executive Summary

### Complete K12 Modernization Scope

Timeline: October 15, 2025 - May 1, 2026 (28 weeks)

Platform Serves:

- Two scholarship programs (ESA+, Opportunity Scholarship)

- Up to 80,000 concurrent users

- Four web portals (Household, School, Provider, Admin)

- Comprehensive scholarship lifecycle management

### Core Capabilities Required

- Household & Student Management (15+ features): This domain covers the core entry points for end-users. Critical features include the ESA+ and OS application workflows, renewal processes, and student profile and account management.

- School Management (20+ features): This focuses on institutional requirements, including school registration and profiles, annual certification workflows, and the crucial, time-sensitive semester parent endorsement process.

- Provider Management (12+ features): This involves managing service providers (tutors, therapists) who accept ESA+ funds. Key features include provider registration and enrollment, the public provider directory, and invoice submission and processing.

- Admin Portal Operations (30+ features): This is the operational core for SEAA staff, enabling application processing and review, verification management (domicile, income, sampling), award management (lottery, calculation, lifecycle), and necessary reporting and analytics.

- Payment & Financial Systems (18+ features): This domain handles the disbursement of scholarship funds. Critical requirements include direct payment school processing, ESA+ wallet and purchasing (which relies heavily on ClassWallet integration), tax reporting (1099-G), rollover management, and minimum spending enforcement ($1,000 threshold for ESA+).

- Verification & Compliance (15+ features): This domain is critical for regulatory adherence and includes eligibility verification workflows, ongoing compliance monitoring, and integrations with 7 state agencies. The mandatory process of verification sampling (4% of applications) and handling non-cooperation falls here.

Critical Deadline: May 1, 2026 - All core functionality must be production-ready

STATUS KEYS:

- NI: NOT IMPLEMENTED

- IP: IN PROGRESS

- SU: STATUS UNKNOWN

- DONE: COMPLETED

### Platform Architecture

- Serverless / Microservices (IP)

  - Azure Functions, API Management, SQL Database

- Event-driven Processing (IP)

  - Event Grid, Azure Functions, Azure Logic Apps

- Business Logic Layer (NI)

  - Rules Engine (IP)

- Analysis & Design (NI)

  - artifacts (diagrams)

  - Azure Network

  - Domain Diagram(s)

- Architecture Decision Record (NI)

- SignalR (for Message Center) (DONE)

- Document Storage (DataLake) (DONE)

FE: responsive architecture/tools/execution

### Tools

- Frontend

  - ADA/WCAG compliance (IP)

  - Jest (unit testing) (IP)

  - UI Control Suite (DONE)

  - Prettier, Pre-Commit Hooks (NI)

  - Nx Console/Generators (NI)

- Backend

  - Rules Engine Framework Selecction (IP)

### Infrastructure

- Network Security (DONE)

- CI/CD Piplelines from development to production (IP)

- Reliability

- Quality

  - Testing

- Security

  - Package scanning (IP)

### Cross-Cutting Concerns Required

- Observability/Telemetry (IP)

- Enrollment Builder (IP)

  - UI Admin, Render Engine, Components

  - Data Mapper

- Entra (DONE)

- Communication Center (DONE)

  - Email

  - In-application notifications

- Query Builder (Cube Core) (IP)

  - reporting

  - ad-hoc queries

  - recipient list generation

- Task Engine (DONE)

- Document Storage (DONE)

  - Versioning

  - Retention

- PandaDocs (DONE)

- Audit Logging (NI)

- PID Generator/Integration (NI)

### 3rd-Party Integration(s)

- ClassWallet (NI)

- RDS (NI)

- SparkPost (Email Engine) (DONE)

- Aperio/CISCO Call Center (Provider Lookup) (NI)

- PandaDocs (DONE)

- Cube Cloud (API and SDK integration) (IP)

### Data Migrations

- Schools (NI)

- Providers (NI)

- Household and Students (NI)

- Operational Data (existing) (NI)

## K-12 SEAA Modernization Project: Technology Roadmap Report

### 1. Definition of a Technology Roadmap

A Technology Roadmap, in the context of the K-12 SEAA Modernization project, is a strategic, phased delivery plan covering the entire scope of work, designed to guide the development teams toward a critical production launch deadline of May 1, 2026.

Based on the materials, the roadmap functions as the implementation plan, detailing the sequential delivery of 110+ distinct features across six core functional domains, the integration of high-risk external systems (like ClassWallet), and the resolution of critical architectural and data integrity deficiencies. The roadmap prioritizes the delivery of cross-cutting services early to ensure the foundation for security (Entra ID), logic (Rules Engine), and communication (Communication Center) is stable before executing advanced administrative and financial workflows.

### 2. Project Context and State of Project

The K-12 SEAA Modernization project has been in development for approximately one year. The project serves two scholarship programs (ESA+ and Opportunity Scholarship) and must support up to 80,000 concurrent users across four web portals (Household, School, Provider, Admin).

#### Core Features

- Status: NOT IMPLEMENTED (NI)

- Challenges: None of the core features are implemented, integrated and/or complete.

  - Registration and application workflows for ESA+ and Opportunity Scholarship

  - Renewal processes

  - School and Provider management portals

  - Admin portal operations for SEAA staff

  - Payment processing and financial systems

  - Verification and compliance workflows, including state agency integrations

  - Database schema for all domains (modernization)

- Resolution:

  - Implement workflow-centric operations to deliver core features in a phased manner over the next 7 months.

  - Start with foundational features (i.e., Student, Household, School, Provider) and logical sequence(s)

    - Stop focus on tool-building

    - Stop focus on "what is easy" (e.g., Provider)

  - Focus on event-driven workflows to decouple services and improve scalability

    - REQUIRES: grouping tasks to operational workflows with application context

  - Prioritize high-risk external integrations (ClassWallet, RDS) early in the roadmap

  - Need application database and resources to enforce relational integrity and domain-driven design

    - Implement a coordination of database schemas, changes, and environment deployments

#### Architecture (Backend)

- Status: NI / IN PROGRESS (IP)

- Challenges:

  - Process: Architecture Design, Analysis, and Decision Records (NI)

  - Business Logic Layer (NI)

  - Workflow and Event-driven Processing (IP)

  - Strong Business Logic with Rules Engine (IP)

- Resolution:

  - Complete Architecture Decision Records (ADRs) for all major design decisions

  - Finalize Business Logic Layer design using Rules Engine

  - Fully implement event-driven architecture with Workflow-centric operations and Task Engine

    - REQUIRES: grouping tasks to operational workflows with application context

#### Architecture (Frontend)

- Status: New

- Challenges:

  - (4) autonomous teams working in silos without architectural governance

  - Consistent components communication (i.e., API, responses ) patterns not established

  - Enterprise cross-cutting concerns (i.e., logging, error handling, telemetry) not implemented/standardized

- Resolution:

  - (1) Frontend Architect to coordinate implementation of patterns, components, and shared libraries

    - Adding core cross-cutting concerns (i.e., logging, error handling, and configuration)

  - Document and socialize standards for API contracts, responses, and error handling

  - Establish architectural governance process for all teams to follow

  - Implement shared libraries for cross-cutting concerns and utilities

    - shared models and DTO library projects

    - shared layout and styles/assets library projects

    - Data access layer with repository pattern (i.e., Http Service)

#### Cross-Cutting Services

- Status: DONE / IP

- Details:

  - Microsoft Entra (Security) (DONE)

  - Communication Center (DONE)

  - SignalR (DONE)

  - PandaDocs (DONE)

  - Document Storage (DONE)

  - Rules Engine (IP)

  - Observability/Telemetry (IP).

- Resolution:

  - Complete implementation and integration of Rules Engine with business logic

  - Finalize Observability/Telemetry for end-to-end monitoring and diagnostics

    - AppInsights, Log Analytics, Distributed Tracing

    - by Application (i.e., frontend and backend), environment

    - monitoring dashboards and alerts (thresholds)

#### 3rd-Party Integrations

- Status: NI / DONE / IP

- Details:

  - SparkPost (Email Engine) (DONE)

  - PandaDocs (DONE)

  - ClassWallet (NI)

  - State Agency Integrations (RDS) (NI)

  - Aperio/CISCO Call Center (NI)

- Resolution:

  - Prioritize ClassWallet and RDS integrations early in the roadmap due to high risk

  - Establish integration patterns and error handling strategies for external systems

#### Data & Data Migration

- Status: NOT IMPLEMENTED (NI)

- Details:

  - Migrations for Schools (NI)

  - Providers (NI)

  - Household

  - Students (NI)

  - and Operational Data (NI) are all pending

- Resolution:

  - Implement and/or stabilize the modernization schema(s)

    - Need resource(s) to lead schema design and enforcement

  - Develop comprehensive data migration strategy and tools

    - Need resource(s) to lead schema design and enforcement

    - Prioritize migrations based on feature delivery roadmap to ensure data availability for core functionalities

|

### 3. Critical Risk Assessment and Mitigation

The project faces several HIGH RISK areas that could jeopardize the May 1, 2026 deadline.

| Critical Risk | Challenge | Mitigation Strategy |
| --- | --- | --- |
| ClassWallet Integration | High vendor dependency for all ESA+ wallet, purchasing, and expense management workflows in Phase 4. | Use Idempotency keys for all transactions and perform rigorous sandbox testing early. |
| Database Schemas | High risk due to lack of resources and/or expertise in modernizing legacy schemas. | Execute a Rapid Assessment and Remediation plan to identify and address schema issues in parallel with development efforts. Focus on foundational data schemas first. |
| Legacy Data Migration | High risk due to legacy data quality, volume, and the current schema's lack of relational integrity. | Execute a Phased Migration by Bounded Context rather than a single "Big Bang" approach to reduce risk and allow for iterative validation. |